## Sign-off
FPV-D6 — FPGA verification signoff report
Sign-off for FPV-D6, produced by FPV-06 FPGA Verification Signoff. Work through the Checklist first; this sheet counts it. See Guide for how to use the workbook.
Document control
Programme
Deliverable | FPV-D6 — FPGA verification signoff report
Stage | FPGA Prototype Verification
Producing activity | FPV-06 — FPGA Verification Signoff
Activity owner | FPGA verification lead
Version
Date issued for review
Readiness — counted from the Checklist
Items to confirm | 23
Owner status — Pass | 0
Owner status — Waived | 0
Owner status — N/A | 0
Owner status — Fail | 0
Owner status — Open or blank | 23
Stage lead — Confirmed | 0
Stage lead — Rejected | 0
Stage lead — Pending or blank | 23
Confirmed so far | 0%
Rows flagged on the Checklist | 0
Critical or High issues still Open | 0
Waivers without an approver | 0
Suggested outcome | In review
Final decision — stage lead
Decision
Conditions (if any)
Stage lead
Decided on
Consistency check
Sign-off by role
Role | Name | Decision | Date | Comment
FPGA verification lead
Verification lead
Firmware lead
Chief architect
Program manager

## Checklist
FPV-D6 checklist — confirm every item on its evidence
Owners fill Result, Evidence, Evidence owner and Owner status. The stage lead then confirms or rejects each item. Yellow cells are for input; grey cells come from the template. The Flag column names any row that cannot yet be confirmed as filled in.
ID | Section | Item | Target / acceptance | Result or measured value | Evidence — link or file name | Evidence owner | Owner status | Waiver ID | Stage lead confirmation | Stage lead comment | Confirmed on | Flag
B-01 | Baseline | Final RTL tag including every ECO | Version, tag or ID recorded |  |  |  | Open |  | Pending
B-02 | Baseline | FPGA image ID built from that tag | Version, tag or ID recorded |  |  |  | Open |  | Pending
B-03 | Baseline | Test list version (FPV-D1) | Version, tag or ID recorded |  |  |  | Open |  | Pending
B-04 | Baseline | Compiler and SDK versions used | Version, tag or ID recorded |  |  |  | Open |  | Pending
E-01 | Entry criteria | Final RTL with all ECOs tagged in ERTL-02 | Met |  |  |  | Open |  | Pending
E-02 | Entry criteria | Every test on the list run in FPV-04 | Met |  |  |  | Open |  | Pending
E-03 | Entry criteria | Open-issue list current in FPV-05 | Met |  |  |  | Open |  | Pending
C-01 | Checks | Full regression on the tapeout RTL | All tests run |  |  |  | Open |  | Pending
C-02 | Checks | Test list pass rate | At or above the exit criterion |  |  |  | Open |  | Pending
C-03 | Checks | Peripheral interoperability with real devices and shields | Pass |  |  |  | Open |  | Pending
C-04 | Checks | Boot paths — eMRAM, UART, SPI flash, JTAG, secure boot | Pass |  |  |  | Open |  | Pending
C-05 | Checks | Compiled workloads against the simulator | Results match |  |  |  | Open |  | Pending
C-06 | Checks | Soak and stability run | Hours met without failure |  |  |  | Open |  | Pending
C-07 | Checks | SDK driver and RTOS regression | Pass |  |  |  | Open |  | Pending
C-08 | Checks | Open FPGA bugs | Each fixed, or waived with a workaround and owner |  |  |  | Open |  | Pending
X-01 | Exit criteria | Full regression passed on the tapeout RTL | Met |  |  |  | Open |  | Pending
X-02 | Exit criteria | Every exit criterion met or waived with a workaround and owner | Met |  |  |  | Open |  | Pending
X-03 | Exit criteria | Signoff report entered in the tapeout checklist before the Go / No-Go | Met |  |  |  | Open |  | Pending
F-01 | Failure modes | Regression run on an RTL that is not the tapeout RTL. A late ECO lands after the run, and the signoff certifies a design that is not the one going to mask. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-02 | Failure modes | Exit criteria renegotiated at the end. Criteria lowered to meet the date make the signoff decorative and move the risk to first silicon. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-03 | Failure modes | Open issues waived without a workaround. A waiver needs a silicon, SDK or errata plan with an owner, or it is a bug accepted blind. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-04 | Failure modes | Blind spots not restated. The report must repeat what the FPGA could not show, so the tapeout review does not read FPGA signoff as proof of power gating or analog behaviour. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-05 | Failure modes | Signoff too close to the Go / No-Go. Two weeks leave no time to fix anything the final regression finds, so the final run starts as soon as the last ECO lands. | Addressed — say how in the result |  |  |  | Open |  | Pending

## Open issues
Open issues
Anything that stops an item being confirmed. Link it to the checklist item it blocks. A Critical or High issue left Open blocks the sign-off.
Issue ID | Description | Linked item ID | Severity | Owner | Due | Status | Disposition

## Waivers
Waivers
Every item whose Owner status is Waived needs a row here, and every waiver needs an approver. A waiver without one blocks the sign-off.
Waiver ID | Linked item ID | Check or rule waived | Justification | Risk accepted | Condition or expiry | Approved by | Approved on

## What the prototype could not sh
What the prototype could not show
Restate the blind spots from FPV-D2 and who covers each — power gating, analog behaviour, silicon timing.
Blind spot | Covered by | Owner

## Handover
Handover
Who receives FPV-D6, and what they take from it. The receiving owner records receipt.
Receiving activity | What it takes from this deliverable | Received by | Received on
ETO-03 — Tapeout Checklist Completion and Owner Signoff
ETO-04 — Open-Issue Risk Assessment and Waiver Acceptance
ETO-05 — Go / No-Go Decision Meeting

## Guide
How to use this workbook
FPV-D6 is signed off on evidence, item by item. This sheet says who fills what.
1. Owners | On the Checklist, for each item: write the Result or measured value, the Evidence (a link to the report, dashboard or file name), who owns that evidence, and set Owner status. Waived needs a Waiver ID that exists on the Waivers sheet.
2. Stage lead | Review each item against its evidence. Set Stage lead confirmation to Confirmed, or Rejected with a comment saying what is missing. Date every confirmation.
3. Flags | The Flag column names any row that is not yet supported: evidence missing, a waiver without an ID, a rejection without a comment, a confirmation of a failing item, or an undated confirmation. Clear every flag.
4. Issues and waivers | Record anything blocking an item on Open issues, linked by item ID. A Critical or High issue left Open, or a waiver without an approver, holds the gate.
5. Final decision | The Sign-off sheet counts the Checklist and suggests an outcome. The stage lead records the Decision, any conditions, and the date. Each role then records its own decision.
6. Handover | Attach the completed workbook to this deliverable's Handover in AtlasPM and date the handover when it is accepted.
Yellow cells | Input — fill these in.
Grey cells | Given by the template from the activity write-up — do not edit.
Owner status | Pass — meets the target. Fail — does not. Waived — does not, and a waiver accepts it. N/A — does not apply, with the reason in Result. Open — not yet assessed.
Lead confirmation | Pending — not yet reviewed. Confirmed — the evidence supports the status. Rejected — it does not; the comment says why.
Example row
Item | Macro pin timing — setup and hold, all signoff corners
Target | Within vendor limits, no negative slack
Result | Worst setup slack +42 ps (ss_0p72v_125c); worst hold +18 ps (ff_0p88v_m40c)
Evidence | sta/turn3/emram_pins_summary.rpt (run 2027-05-14)
Evidence owner | Timing closure lead
Owner status | Pass
Stage lead | Confirmed — 2027-05-16