## Sign-off
ESO-D7 — Signoff summary and Design Freeze package
Sign-off for ESO-D7, produced by ESO-11 Waiver Review Board and Foundry Waiver Alignment. Work through the Checklist first; this sheet counts it. See Guide for how to use the workbook.
Document control
Programme
Deliverable | ESO-D7 — Signoff summary and Design Freeze package
Stage | Signoff
Producing activity | ESO-11 — Waiver Review Board and Foundry Waiver Alignment
Activity owner | Signoff lead
Version
Date issued for review
Readiness — counted from the Checklist
Items to confirm | 23
Owner status — Pass | 0
Owner status — Waived | 0
Owner status — N/A | 0
Owner status — Fail | 0
Owner status — Open or blank | 23
Stage lead — Confirmed | 0
Stage lead — Rejected | 0
Stage lead — Pending or blank | 23
Confirmed so far | 0%
Rows flagged on the Checklist | 0
Critical or High issues still Open | 0
Waivers without an approver | 0
Suggested outcome | In review
Final decision — stage lead
Decision
Conditions (if any)
Stage lead
Decided on
Consistency check
Sign-off by role
Role | Name | Decision | Date | Comment
Signoff lead
Domain signoff owners
Foundry liaison
Chief architect
Program manager

## Checklist
ESO-D7 checklist — confirm every item on its evidence
Owners fill Result, Evidence, Evidence owner and Owner status. The stage lead then confirms or rejects each item, naming who confirmed it and when. Yellow cells are for input; grey cells come from the template. The Flag column names any row that cannot yet be confirmed as filled in.
ID | Section | Item | Target / acceptance | Result or measured value | Evidence — link or file name | Evidence owner | Owner status | Waiver ID | Stage lead confirmation | Stage lead comment | Confirmed by | Confirmed on | Flag
B-01 | Baseline | Final database signed off (version and checksum) | Version, tag or ID recorded |  |  |  | Open |  | Pending
B-02 | Baseline | Signoff deck versions per domain | Version, tag or ID recorded |  |  |  | Open |  | Pending
B-03 | Baseline | Foundry waiver submission references | Version, tag or ID recorded |  |  |  | Open |  | Pending
E-01 | Entry criteria | Signoff activities producing waiver candidates | Met |  |  |  | Open |  | Pending
E-02 | Entry criteria | Foundry waiver process understood from ETECH-03 | Met |  |  |  | Open |  | Pending
E-03 | Entry criteria | Board membership named with authority to refuse | Met |  |  |  | Open |  | Pending
C-01 | Checks | Static timing — all corners and modes | Signed off |  |  |  | Open |  | Pending
C-02 | Checks | DRC, LVS, antenna and density | Clean or waived |  |  |  | Open |  | Pending
C-03 | Checks | EM / IR | Signed off |  |  |  | Open |  | Pending
C-04 | Checks | ESD, latch-up and FIT | Signed off |  |  |  | Open |  | Pending
C-05 | Checks | DFM and lithography hotspots | Signed off |  |  |  | Open |  | Pending
C-06 | Checks | Signal integrity | Signed off |  |  |  | Open |  | Pending
C-07 | Checks | Final formal equivalence | Equivalent |  |  |  | Open |  | Pending
C-08 | Checks | Gate-level simulation with final SDF | Passing |  |  |  | Open |  | Pending
C-09 | Checks | Leakage and sleep current against the budget | Within budget |  |  |  | Open |  | Pending
X-01 | Exit criteria | Every waiver has a root cause, a quantified risk and a signature | Met |  |  |  | Open |  | Pending
X-02 | Exit criteria | Foundry waivers submitted and answered before freeze | Met |  |  |  | Open |  | Pending
X-03 | Exit criteria | Residual risk summarized in one statement for the gate | Met |  |  |  | Open |  | Pending
F-01 | Failure modes | Waivers accumulated rather than reviewed. A register nobody dispositioned is a set of accepted risks nobody accepted. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-02 | Failure modes | Foundry waivers submitted late. Their review is on the foundry's schedule, and an unapproved waiver blocks mask release. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-03 | Failure modes | Risk quantified qualitatively. "Low risk" is not a basis for a tapeout decision; a stated failure mode and probability is. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-04 | Failure modes | Board without authority. A review that cannot refuse a waiver is a review that approves everything. | Addressed — say how in the result |  |  |  | Open |  | Pending
F-05 | Failure modes | Residual risk not summarized. The Go / No-Go decision needs one statement of what is being accepted, not a register of two hundred entries. | Addressed — say how in the result |  |  |  | Open |  | Pending

## Open issues
Open issues
Anything that stops an item being confirmed. Link it to the checklist item it blocks. A Critical or High issue left Open blocks the sign-off.
Issue ID | Description | Linked item ID | Severity | Owner | Due | Status | Disposition

## Waivers
Waivers
Every item whose Owner status is Waived needs a row here, and every waiver needs an approver. A waiver without one blocks the sign-off.
Waiver ID | Linked item ID | Check or rule waived | Justification | Risk accepted | Condition or expiry | Approved by | Approved on

## Residual risk statement
Residual risk statement
One statement for the gate: what risk the design is frozen with, and why it is accepted.
Residual risk | Accepted because | Owner

## Handover
Handover
Who receives ESO-D7, and what they take from it. The receiving owner records receipt.
Receiving activity | What it takes from this deliverable | Received by | Received on
ETO-03 — Tapeout Checklist Completion and Owner Signoff
ETO-04 — Open-Issue Risk Assessment and Waiver Acceptance
ETO-05 — Go / No-Go Decision Meeting
EMP-12 — Production Readiness Review and Change Control (PCN) Setup

## Guide
How to use this workbook
ESO-D7 is signed off on evidence, item by item. This sheet says who fills what.
1. Owners | On the Checklist, for each item: write the Result or measured value, the Evidence (a link to the report, dashboard or file name), who owns that evidence, and set Owner status. Waived needs a Waiver ID that exists on the Waivers sheet.
2. Stage lead | Review each item against its evidence. Set Stage lead confirmation to Confirmed, or Rejected with a comment saying what is missing. Name who confirmed it in Confirmed by, and date every confirmation.
3. Flags | The Flag column names any row that is not yet supported: evidence missing, a waiver without an ID, a rejection without a comment, a confirmation of a failing item, a confirmation or rejection nobody put their name to, or an undated confirmation. Clear every flag.
4. Issues and waivers | Record anything blocking an item on Open issues, linked by item ID. A Critical or High issue left Open, or a waiver without an approver, holds the gate.
5. Final decision | The Sign-off sheet counts the Checklist and suggests an outcome. The stage lead records the Decision, any conditions, and the date. Each role then records its own decision.
6. Handover | Attach the completed workbook to this deliverable's Handover in AtlasPM and date the handover when it is accepted.
Yellow cells | Input — fill these in.
Grey cells | Given by the template from the activity write-up — do not edit.
Owner status | Pass — meets the target. Fail — does not. Waived — does not, and a waiver accepts it. N/A — does not apply, with the reason in Result. Open — not yet assessed.
Lead confirmation | Pending — not yet reviewed. Confirmed — the evidence supports the status. Rejected — it does not; the comment says why.
Example row
Item | Macro pin timing — setup and hold, all signoff corners
Target | Within vendor limits, no negative slack
Result | Worst setup slack +42 ps (ss_0p72v_125c); worst hold +18 ps (ff_0p88v_m40c)
Evidence | sta/turn3/emram_pins_summary.rpt (run 2027-05-14)
Evidence owner | Timing closure lead
Owner status | Pass
Stage lead | Confirmed — 2027-05-16